## Open Issues
Rent-A-Vacation — Open GitHub Issues
Repo: rent-a-vacation/rav-website · Generated 2026-04-26 · 49 open issues
# | Title | Priority | Type | Area | Milestone | Labels | Assignees | Author | Comments | Created | Updated | URL | Summary
127 | Business Formation & Stripe Tax Activation | blocked |  | platform |  | blocked, needs-decision, platform, pre-launch |  | jisujit | 1 | 2026-02-26 | 2026-04-18 | https://github.com/rent-a-vacation/rav-website/issues/127 | ## Summary Stripe Tax cannot be fully activated until a business entity is formed and state tax registrations are obtained. This is a **pre-launch blocker** — the platform cannot legally collect and remit sales/occupancy tax on vacation rental bookings without proper business registration. ## Current State - **Stripe account:** Personal account (not business) - **Business entity:** Not yet formed - **Tax registrations:** None - **Stripe Tax status:** Not activated (setup partially started — hea…
63 | Phase 20E: Accounting Integration (Puzzle.io → pluggable) | blocked | enhancement | platform | Phase 20: Accounting & Tax | blocked, enhancement, platform, post-launch |  | jisujit | 1 | 2026-02-24 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/63 | ## Accounting Integration — Pluggable Provider Architecture **Primary provider:** Puzzle.io (native Stripe integration, free tier <$20K/mo) **Architecture:** Provider-agnostic adapter pattern — swap to QuickBooks, Xero, or Zoho Books via configuration ### Why Puzzle.io over QuickBooks ¦ Criteria ¦ Puzzle.io ¦ QuickBooks Online ¦ ¦----------¦-----------¦-------------------¦ ¦ **Stripe integration** ¦ Native API — 98% auto-categorization ¦ Via Synder/Zapier middleware ¦ ¦ **Free tier** ¦ Yes — <$…
438 | Incorporation documentation starter kit — operating agreement, formation docs, Stripe samples | pre-launch | docs |  |  | docs, pre-launch |  | jisujit | 0 | 2026-04-24 | 2026-04-24 | https://github.com/rent-a-vacation/rav-website/issues/438 | ## Context RAV is pre-incorporation (#127 blocks Stripe Tax, bank, Puzzle.io accounting, legal ToS, A2P 10DLC SMS). Before / during the LLC formation pass, the founding team needs a starter library of legal-and-operational documents: operating agreement, founder understanding, equity-if-applicable language, customer terms templates. Two practical sources: - **Stripe Atlas** (and similar: Clerky, LegalZoom, Firstbase) publishes high-quality templates that most early-stage companies start from — …
257 | Legal: Audit scraped resort data for compliance — review seed data sources | pre-launch | bug | platform |  | bug, platform, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/257 | # Audit Scraped Resort Data for Legal Compliance ## Context During early development, public data from resort brand websites (Hilton, Marriott, Disney, etc.) was collected to seed the platform with resort/property information — names, locations, amenity descriptions, and potentially images. This data was used to populate the initial brand, vacation property, and location records. **Before production launch, we must ensure this data usage is legally compliant.** ## Risk Assessment ¦ Data Type ¦ …
256 | Pitch deck & investor presentation materials | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/256 | # Pitch Deck & Investor Presentation Materials **Parent epic:** #250 ## Objective Create professional, VC-ready presentation materials that clearly communicate RAV's value proposition, market opportunity, competitive advantages, and traction. These materials serve multiple audiences: investors, potential partners, resort operators, and team recruitment. ## Deliverables ### 1. Pitch Deck (10-15 slides) - [ ] **Cover:** Rent-A-Vacation — tagline, logo, brand colors - [ ] **Problem:** Timeshare ow…
255 | Market Research: Industry reports & ARDA data collection | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/255 | # Industry Reports & ARDA Data Collection **Parent epic:** #250 ## Objective Gather authoritative industry data to support pitch deck claims, understand market size, and identify trends. VCs expect data-backed assertions about the market. ## Key Data Points Needed ### Market Size & Scope - [ ] Total US timeshare market value (~$10B+ annually) - [ ] Number of timeshare owners in the US (~9.6M per ARDA) - [ ] Average annual maintenance fee ($1,120+ and rising) - [ ] Percentage of weeks that go un…
254 | Market Research: Google Trends & keyword research for timeshare rental demand | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/254 | # Google Trends & Keyword Research **Parent epic:** #250 ## Objective Understand search demand for timeshare rentals, identify seasonal patterns, and find the keywords that potential users are actually searching for. This informs SEO strategy, ad campaigns, and content marketing. ## Research Tasks ### Google Trends Analysis - [ ] Compare search interest: \"timeshare rental\" vs \"rent timeshare\" vs \"timeshare for rent\" - [ ] Compare: \"vacation rental\" vs \"timeshare rental\" vs \"resort re…
253 | Market Research: Review mining — extract insights from competitor reviews | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/253 | # Review Mining — Competitor Review Analysis **Parent epic:** #250 ## Objective Analyze public reviews of competitor platforms to identify unmet user needs, common complaints, and feature requests — then validate that RAV addresses them. ## Sources to Mine ### App Store Reviews (if mobile apps exist) - [ ] Koala — iOS App Store + Google Play - [ ] RedWeek — iOS App Store + Google Play - [ ] Timeshares Only — check for apps - [ ] VRBO / Airbnb — focus on timeshare-specific complaints ### Web Rev…
252 | Market Research: Mystery shopping — create accounts on competitor platforms | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/252 | # Mystery Shopping — Competitor Platform Experience **Parent epic:** #250 ## Objective Experience competitor platforms as both an owner and a traveler to identify UX strengths, pain points, and opportunities for RAV differentiation. ## Approach ### As a Traveler (on each platform) - [ ] Create a renter account — note signup friction (how many steps? verification needed?) - [ ] Search for a specific destination (e.g., Orlando, 2 bedroom, July dates) - [ ] Browse listing detail pages — what info …
251 | Market Research: Feature comparison matrix — RAV vs. competitors | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/251 | # Feature Comparison Matrix — RAV vs. Competitors **Parent epic:** #250 ## Objective Build a detailed feature-by-feature comparison of RAV against all known competitors. This becomes source material for the pitch deck, website marketing copy, and partner conversations. ## Comparison Dimensions ### Business Model - [ ] Commission / fee structure (what % does each platform take?) - [ ] Who pays — owner, renter, or both? - [ ] Payment handling (escrow, direct, off-platform?) - [ ] Pricing model (p…
250 | Epic: Market Research & Competitive Analysis | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/250 | # Epic: Market Research & Competitive Analysis ## Objective Conduct thorough market research to understand the competitive landscape, validate RAV's positioning, and build materials for VC conversations, partner discussions, and go-to-market strategy. ## Why Now - VCs and potential partners are asking questions about market positioning - Need to articulate differentiation clearly in pitch materials - Post-launch strategy should be informed by what competitors do well and poorly - Team alignment…
234 | Marketing: Google Business Profile setup for local search & brand visibility | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/234 | ## Objective Create a Google Business Profile for Rent-A-Vacation to improve brand search visibility, appear in Google's knowledge panel, and build trust with searchers. ## Why Google Business Profile (often overlooked, high impact) - When someone Googles "Rent A Vacation", a Google Business Profile shows a knowledge panel on the right side of search results — logo, description, website link, reviews - Establishes legitimacy immediately (users trust businesses with Google profiles) - Free and t…
232 | Marketing: LinkedIn Company Page setup for B2B credibility | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/232 | ## Objective Establish Rent-A-Vacation's LinkedIn Company Page for B2B credibility, investor relations, and professional networking with resort partners. ## Why LinkedIn - First place investors and potential partners check for legitimacy - Property management companies and resort operators are active on LinkedIn - Founder thought leadership builds trust in the timeshare disruption narrative - Required for professional recruitment as the team grows ## Setup tasks ### Company Page - [ ] Create Li…
231 | Marketing: Instagram Business Account setup & visual content strategy | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/231 | ## Objective Establish Rent-A-Vacation's Instagram presence as the visual showcase channel targeting travelers and aspirational vacation seekers. ## Why Instagram - Visual-first platform — resort photos and vacation lifestyle content perform exceptionally well - Reels and Stories drive discovery among travelers researching destinations - Instagram Shopping / link-in-bio drives direct traffic to listings - Shared ad infrastructure with Facebook via Meta Business Suite ## Setup tasks ### Account …
230 | Marketing: Facebook Business Page setup & launch content | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/230 | ## Objective Establish Rent-A-Vacation's Facebook Business Page as the primary social channel for property owners and travelers aged 35+. ## Why Facebook - Largest audience overlap with timeshare owners (median age 45-65) - Facebook Groups are where timeshare owners discuss rentals, fees, and frustrations - Business Page is required for Facebook/Instagram Ads (Meta Business Suite) - Marketplace-style businesses get strong organic reach via shares and recommendations ## Setup tasks ### Account &…
213 | Digital Marketing: Social media presence setup (Facebook, Instagram, LinkedIn, X) | pre-launch | enhancement | experience |  | enhancement, experience, pre-launch |  | jisujit | 0 | 2026-03-14 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/213 | ## Summary **This is the parent tracking issue** for social media and digital presence setup across all platforms. Each platform has its own detailed, assignable story below. ## Platform stories ¦ # ¦ Platform ¦ Priority ¦ Assignable to ¦ Status ¦ ¦---¦----------¦----------¦---------------¦--------¦ ¦ #230 ¦ Facebook Business Page ¦ P0 — pre-launch ¦ Any founder ¦ Open ¦ ¦ #231 ¦ Instagram Business Account ¦ P0 — pre-launch ¦ Any founder ¦ Open ¦ ¦ #232 ¦ LinkedIn Company Page ¦ P1 — pre-launch…
187 | Pre-launch: remaining manual verification items before Go Live | pre-launch |  | platform | Launch Readiness | platform, pre-launch |  | jisujit | 0 | 2026-03-07 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/187 | ## Context The Launch Readiness checklist and Go Live tooling were built in #87. These are the remaining items that must be completed **before flipping Staff Only Mode off**. The Launch tab in Admin Dashboard will show these as failing/manual until resolved. ## Blocked items (waiting on external) - [ ] **Stripe live mode** — `STRIPE_SECRET_KEY` must be `sk_live_*` on PROD Supabase secrets. Blocked on #127 (LLC/EIN → Stripe activation) - [ ] **Legal pages reviewed** — /terms and /privacy exist b…
80 | Legal review: Terms of Service and Privacy Policy | pre-launch | bug | platform | Launch Readiness | bug, platform, pre-launch |  | jisujit | 1 | 2026-02-25 | 2026-04-21 | https://github.com/rent-a-vacation/rav-website/issues/80 | ## Problem `Terms.tsx` and `Privacy.tsx` say "Last updated: February 2025" and appear to be generic placeholders, not reviewed by legal counsel for a marketplace handling payments and PII across states. ## Tasks - [ ] Engage legal counsel for marketplace-specific ToS review - [ ] Cover: marketplace facilitator obligations, escrow/payment terms, limitation of liability, dispute resolution, cancellation policies - [ ] Cover: state-specific requirements (43+ states for tax) - [ ] Privacy Policy mu…
444 | Add edge-fn tests for notification stack (notification-dispatcher, sms-scheduler, twilio-webhook) | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-04-25 | 2026-04-25 | https://github.com/rent-a-vacation/rav-website/issues/444 | ## Context The 3 notification edge fns (\`notification-dispatcher\`, \`sms-scheduler\`, \`twilio-webhook\`) ship to DEV but are blocked on A2P 10DLC SMS registration (#127 LLC/EIN chain) before they handle production traffic. Session 60 / #371 (PR #441) established the Vitest harness pattern but kept this stack out of scope since it can't be exercised in PROD until #127 clears. ## Goal Apply the Vitest harness pattern to all 3 notification edge fns so they have automated coverage when A2P 10DLC…
370 | Platform Monitoring: Synthetic uptime checks via Checkly (SaaS) | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-04-18 | 2026-04-18 | https://github.com/rent-a-vacation/rav-website/issues/370 | ## Context Sentry.io covers error tracking + performance when users hit issues, but it does not do **synthetic uptime monitoring** — i.e. proactively checking that critical user journeys still work when no one happens to be using the site. Before launch (web + mobile), we want a single dashboard to see the health of the platform 24/7. ## Decision: Checkly (public SaaS, free tier) Evaluated options: ¦ Tool ¦ Type ¦ Verdict ¦ ¦------¦------¦---------¦ ¦ **Checkly** ¦ Synthetic browser + API check…
368 | Tier value enhancements: faster payouts, cancellation upgrades, seasonal pricing | post-launch | enhancement | marketplace |  | enhancement, marketplace, post-launch |  | jisujit | 0 | 2026-04-18 | 2026-04-18 | https://github.com/rent-a-vacation/rav-website/issues/368 | ## Context Supersedes #166. The original issue identified gaps in membership tier value beyond voice quotas and commission discounts. Most of the proposed enhancements have now been shipped: ### Already Implemented (via #278-#282) - ✅ Early access to new listings (Traveler Plus) - ✅ Exclusive deals / member-only pricing (Traveler Premium) - ✅ Priority listing placement / featured badge (Owner Pro) - ✅ Concierge support (Traveler Premium) - ✅ Dedicated account manager (Owner Business) - ✅ Price …
233 | Marketing: X (Twitter) profile setup for industry presence & support | post-launch | enhancement | experience |  | enhancement, experience, post-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/233 | ## Objective Establish Rent-A-Vacation's X/Twitter presence for industry news, customer support, and real-time engagement. ## Why X (lower priority than Facebook/Instagram/LinkedIn) - Industry conversations and travel deal hunting happen on X - Quick customer support channel (public responses build trust) - Proptech and startup communities are active on X - Good for SEO (Twitter profiles rank in Google for brand searches) ## Setup tasks ### Account & branding - [ ] Create X account (target hand…
227 | Sentry: Instrument Supabase edge functions for server-side error tracking | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-21 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/227 | ## Context Sentry is currently frontend-only (`@sentry/react`). Our 30 Supabase edge functions (Deno runtime) have no error tracking — failures are only visible in Supabase function logs, which are ephemeral and lack alerting. ## What to build 1. **Sentry Deno SDK** integration for edge functions (or lightweight HTTP transport) 2. **Shared helper** in `supabase/functions/_shared/sentry.ts` — init + captureException wrapper 3. **Instrument critical edge functions first:** - `stripe-webhook` (pay…
225 | Set up Slack workspace for partner discussions | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-19 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/225 | ## Problem WhatsApp group is cluttered — key business decisions get buried. Need structured, searchable, threaded discussions between partners. ## Recommendation Slack free tier with focused channels: - `#decisions` — one post per decision, threaded, pin when resolved - `#launch-blockers` — LLC, legal, verification (high signal only) - `#marketing` — social, content, brand - `#general` — everything else Keep WhatsApp for casual/urgent pings only. Rule: if it needs a decision or needs to be foun…
214 | Digital Marketing: Content strategy & campaign planning | post-launch | enhancement | experience |  | enhancement, experience, post-launch |  | jisujit | 0 | 2026-03-14 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/214 | ## Summary Develop a structured digital marketing strategy covering content calendar, ad campaigns, and growth tactics for post-launch. ## Scope ### Content Marketing - [ ] Blog section on website (#107) — SEO-driven articles - [ ] Email marketing campaigns (#106) — onboarding drips, re-engagement - [ ] Monthly newsletter template - [ ] Resort spotlight series (leverage 117 resort partnerships) ### Paid Advertising - [ ] Facebook/Instagram ad strategy (target: timeshare owners + vacation renter…
192 | API: SDK packages for partners (npm, Python) | post-launch | enhancement | platform |  | enhancement, idea, platform, post-launch |  | jisujit | 0 | 2026-03-10 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/192 | ## Context Partners currently use the raw REST API directly. SDK packages would provide typed, ergonomic wrappers for common languages. ## Scope - `@rav/api-client` npm package (TypeScript, auto-generated from OpenAPI spec) - `rav-api` Python package (for data-oriented partners) - Auto-generated from `docs/api/public-api.yaml` using OpenAPI Generator - Published to npm / PyPI - Includes type definitions, pagination helpers, error handling ## Why not now - Zero partners using the API yet - Raw R…
191 | API: Chat endpoint (/v1/chat) via gateway | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-10 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/191 | ## Context The Public API gateway (#174) was built with 5 read-only endpoints. A `/v1/chat` endpoint was planned (Phase B3) but deferred because it requires extracting the text-chat logic into a shared module first. ## Scope 1. Extract core chat logic from `supabase/functions/text-chat/index.ts` into `_shared/text-chat-handler.ts`: - System prompt selection - OpenRouter API call with tool definitions - SSE event streaming - Search tool execution 2. Refactor existing `text-chat/index.ts` to impo…
190 | API: Webhook delivery to partners (event notifications) | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-10 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/190 | ## Context Partners currently must poll the API to detect changes (new listings, price updates, booking status changes). Webhook delivery would push events to partner endpoints in real-time. ## Scope - Webhook registration in admin dashboard (URL, events, secret) - Event types: `listing.created`, `listing.updated`, `listing.expired`, `booking.confirmed`, `booking.cancelled`, `price.changed` - HMAC signature verification (like Stripe webhooks) - Retry logic with exponential backoff (3 attempts) …
189 | API: OAuth2 authentication for partner integrations | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-10 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/189 | ## Context The Public API currently uses simple API keys (`X-API-Key` header) for partner auth. OAuth2 was deferred as unnecessary for read-only access, but will be needed when write endpoints (#187) are added. ## Scope - OAuth2 authorization code flow for partner applications - Client ID / Client Secret registration in admin dashboard - Token endpoint (`/oauth/token`) with refresh tokens - Scope-based consent screen - Token revocation endpoint ## Why not now - API keys are sufficient for read-…
188 | API: Write endpoints (create bookings, submit bids via API) | post-launch | enhancement | platform |  | enhancement, platform, post-launch |  | jisujit | 0 | 2026-03-10 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/188 | ## Context The Public API (v1) launched with read-only endpoints (#174). Write endpoints were intentionally deferred until partner demand validates the need. ## Scope Add write endpoints to the API gateway: - `POST /v1/bookings` — create a booking (triggers Stripe checkout) - `POST /v1/bids` — submit a bid on a listing - `POST /v1/travel-requests` — create a travel request - `PATCH /v1/bookings/:id/cancel` — cancel a booking ## Requirements - All write ops must go through existing business logi…
165 | Owner Volume Discount: tiered commission reduction based on completed bookings | post-launch | enhancement | marketplace |  | enhancement, marketplace, needs-decision, post-launch |  | jisujit | 1 | 2026-03-03 | 2026-04-18 | https://github.com/rent-a-vacation/rav-website/issues/165 | ## Summary Introduce a **volume-based commission discount** for property owners that rewards repeat successful bookings. This is separate from (and stacks with) membership tier discounts. ## Design Decisions ### Trigger Metric - Based on **completed bookings** (payouts received), not active listings - Only counts bookings where the owner received payout — ensures real transactions ### Proposed Tiers (configurable by admin) Individual timeshare owners typically have 1-3 properties, so thresholds…
107 | Blog / content marketing section for SEO | post-launch | enhancement | experience | Growth & Marketing | enhancement, experience, post-launch |  | jisujit | 0 | 2026-02-25 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/107 | ## Summary Build a `/blog` section on the website for SEO-driven content marketing. Educational content about timeshare clubs, destination guides, and "how to save on resort stays" drives organic search traffic and builds domain authority. ## Why a blog matters for RAV - **SEO:** Long-tail keywords like "how to rent a timeshare week" or "Hilton Grand Vacations maintenance fees 2026" drive organic traffic from people who are our exact target audience - **Authority:** Educational content position…
106 | Email marketing: onboarding drips and re-engagement campaigns | post-launch | enhancement | experience | Growth & Marketing | enhancement, experience, post-launch |  | jisujit | 0 | 2026-02-25 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/106 | All emails are currently transactional (via Resend). No onboarding drip, abandoned-checkout recovery, or re-engagement exists. Could use Resend broadcast feature or dedicated ESP like Customer.io.
100 | Apple Sign-In and Facebook OAuth | post-launch | enhancement | platform | Phase 6: Advanced Features | enhancement, platform, post-launch |  | jisujit | 1 | 2026-02-25 | 2026-04-18 | https://github.com/rent-a-vacation/rav-website/issues/100 | Apple Sign-In is required by Apple if you offer any social login and publish to App Store (relevant for Phase 12 Capacitor). Facebook login is common for travel demographics. Supabase supports both providers.
65 | Phase 20F: Automated Tax Filing | post-launch | enhancement | platform | Phase 20: Accounting & Tax | enhancement, platform, post-launch |  | jisujit | 0 | 2026-02-24 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/65 | ## Automated Tax Filing per Jurisdiction When transaction volume justifies the integration cost. ### Tasks - [ ] Avalara or TaxJar integration for auto-filing per jurisdiction - [ ] Quarterly remittance reports ### Reference - DEC-022 - Docs: `docs/RAV-PRICING-TAXES-ACCOUNTING.md` **Est. Time:** 8-16 hours
322 | [WS4] Vacation Wishes — Proposal location enforcement + fast-track property listing | post-beta | enhancement | marketplace, vacation-wishes |  | enhancement, marketplace, post-beta, vacation-wishes | jisujit | jisujit | 0 | 2026-04-11 | 2026-04-11 | https://github.com/rent-a-vacation/rav-website/issues/322 | ## Status **DESIGN COMPLETE — Implementation deferred until after beta launch** This feature is parked until we have 30+ days of real proposal data to validate the assumptions below. The design is locked; only the implementation waits. ## Spec `Features/WS4-Proposal-Logic-Feature-Brief.md` (April 2026) ## Problem Two related gaps in the current Vacation Wishes proposal flow: **Gap 1 — No matching approved property:** Owner browses Vacation Wishes, sees a traveler wants Colorado, but only has Fl…
224 | [FUTURE] One-Time Events Support | future | enhancement | platform |  | enhancement, future, platform |  | jisujit | 0 | 2026-03-16 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/224 | ## Summary Support for one-time (non-recurring) events in the seasonal event system. **No code needed now** — the schema is already ready. ## What Exists - The `recurrence_type` enum already includes `'one_time'` - `seasonal_events` and `event_instances` tables can store one-time events today ## Future Work Needed 1. **UI filter** to show/hide expired one-time instances in the admin Event Calendar tab 2. **Auto-archive logic**: cron job that sets `status = 'past'` for instances where `event_dat…
443 | Add edge-fn test for ingest-support-docs (admin ETL) | unscheduled | enhancement | platform |  | enhancement, platform |  | jisujit | 1 | 2026-04-25 | 2026-04-25 | https://github.com/rent-a-vacation/rav-website/issues/443 | ## Context Phase 22 (Session 57) shipped the \`ingest-support-docs\` edge fn that syncs \`docs/support/**.md\` → \`support_docs\` table. It was untested at ship time. Session 60 / #371 (PR #441) established the Vitest harness pattern but kept this fn out of scope (admin-only ETL, lower risk surface). ## Goal Apply the Vitest harness pattern to \`supabase/functions/ingest-support-docs/index.ts\`. ## Acceptance criteria - [ ] Split into \`handler.ts\` + thin \`index.ts\` wrapper - [ ] Tests cover…
440 | Archive PROJECT-HUB session handoffs 25-54 to COMPLETED-PHASES | unscheduled | docs |  |  | docs |  | jisujit | 0 | 2026-04-25 | 2026-04-25 | https://github.com/rent-a-vacation/rav-website/issues/440 | ## Context `docs/PROJECT-HUB.md` Session Handoff section currently holds Sessions 25-59 (~34 entries). Per `CLAUDE.md` Phase 6 doc-update checklist: > `docs/COMPLETED-PHASES.md` — only at session close, for sessions aging out of PROJECT-HUB. Move session-handoff entries older than ~5 sessions from PROJECT-HUB to this archive. Keep PROJECT-HUB Session Handoff section lean (current + last 5 sessions). This means Sessions **25-54** should be archived out of PROJECT-HUB, leaving Sessions 55-59 inli…
248 | Mobile: App Store submission — iOS App Store & Google Play | unscheduled | enhancement | platform | Phase 12: Native Mobile (Capacitor) | enhancement, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/248 | # App Store Submission — iOS App Store & Google Play **Parent epic:** #240 ## User Story > As a founder, I want RAV listed in the App Store and Play Store so users can discover and install the app, and VCs can see we have a production mobile presence. ## Acceptance Criteria ### Apple App Store - [ ] Enroll in Apple Developer Program ($99/year) — requires LLC for Organization account - [ ] Create App Store Connect listing: - App name: \"Rent-A-Vacation\" - Subtitle: \"Luxury Resorts, Up to 70% O…
247 | Mobile: Offline support & native storage | unscheduled | enhancement | platform | Phase 12: Native Mobile (Capacitor) | enhancement, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/247 | # Offline Support & Native Storage **Parent epic:** #240 ## User Stories > As a traveler browsing listings at a resort with spotty WiFi, I want to still see listings I've already viewed so I can compare options without losing my progress. > As a property owner filling out a listing form on my phone, I want my draft to be saved automatically so I don't lose my work if the app crashes or I lose connection. ## Acceptance Criteria ### Offline listing cache - [ ] Cache recently viewed listings in `@…
246 | Mobile: Deep linking & universal links | unscheduled | enhancement | platform | Phase 12: Native Mobile (Capacitor) | enhancement, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/246 | # Deep Linking & Universal Links **Parent epic:** #240 ## User Stories > As a traveler, I want to tap a shared listing link on my phone and have it open directly in the RAV app (if installed) so I get the best experience. > As a user who received an email notification, I want to tap the link and land on the right screen in the app, not the mobile website. ## Acceptance Criteria ### Universal Links (iOS) / App Links (Android) - [ ] Host `/.well-known/apple-app-site-association` on `rent-a-vacati…
245 | Mobile: Camera integration & image capture for property photos | unscheduled | enhancement | experience | Phase 12: Native Mobile (Capacitor) | enhancement, experience |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/245 | # Camera Integration & Image Capture **Parent epic:** #240 ## User Stories > As a property owner, I want to take photos of my resort unit directly from the app so I can list my property without needing to transfer photos from my camera roll. > As a user completing identity verification, I want to capture my ID document using the camera so I can verify my identity without scanning or emailing documents. ## Acceptance Criteria ### Camera plugin setup - [ ] Install `@capacitor/camera` plugin - [ ]…
244 | Mobile: Push notifications — FCM & APNs integration | unscheduled | enhancement | experience, platform | Phase 12: Native Mobile (Capacitor) | enhancement, experience, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/244 | # Push Notifications — FCM & APNs Integration **Parent epic:** #240 ## User Stories > As a property owner, I want to receive a push notification on my phone when someone makes an offer on my listing so I can respond quickly and not lose the booking. > As a traveler, I want to get a push notification when my offer is accepted so I can complete payment before the hold expires. > As a user, I want to control which push notifications I receive so I'm not overwhelmed. ## Why This Matters Push notifi…
243 | Mobile: Native authentication — biometric login & OAuth deeplinks | unscheduled | enhancement | platform | Phase 12: Native Mobile (Capacitor) | enhancement, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/243 | # Native Authentication — Biometric Login & OAuth Deeplinks **Parent epic:** #240 ## User Stories > As a returning user, I want to unlock the app with Face ID or my fingerprint so I don't have to type my password every time. > As a user signing up with Google, I want the OAuth flow to return me to the app (not the browser) so the experience feels seamless. ## Acceptance Criteria ### Biometric authentication - [ ] Install `@capacitor-community/biometric-auth` or `@capacitor/biometrics` plugin - …
242 | Mobile: UX polish — safe areas, gestures, bottom navigation | unscheduled | enhancement | experience | Phase 12: Native Mobile (Capacitor) | enhancement, experience |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/242 | # Mobile UX Polish **Parent epic:** #240 ## User Story > As a mobile user, I want the app to feel native with proper safe area handling, gesture navigation, and a thumb-friendly bottom tab bar so the experience matches what I expect from iOS and Android apps. ## Acceptance Criteria ### Safe areas & notch handling - [ ] Install `@capacitor/status-bar` plugin - [ ] Apply `env(safe-area-inset-*)` CSS for content padding on notched devices - [ ] Header doesn't overlap with iOS Dynamic Island or And…
241 | Mobile: Capacitor shell & project setup | unscheduled | enhancement | platform | Phase 12: Native Mobile (Capacitor) | enhancement, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/241 | # Capacitor Shell & Project Setup **Parent epic:** #240 ## User Story > As a developer, I want to initialize Capacitor in the existing React project so that the web app can run as a native iOS and Android app with access to device APIs. ## Acceptance Criteria ### Project initialization - [ ] Install Capacitor core: `@capacitor/core`, `@capacitor/cli` - [ ] Run `npx cap init` with app ID `com.rentavacation.app` and name `Rent-A-Vacation` - [ ] Configure `capacitor.config.ts` with webDir pointing…
240 | Epic: Mobile App — iOS & Android via Capacitor | unscheduled | enhancement | experience, platform | Phase 12: Native Mobile (Capacitor) | enhancement, experience, platform |  | jisujit | 0 | 2026-04-02 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/240 | # Mobile App Epic — iOS & Android via Capacitor ## Strategic Context VCs and early partners consistently ask: "Do you have a mobile app?" A native mobile presence signals product maturity, unlocks push notifications (the most effective engagement channel), and provides App Store / Play Store discoverability. **Decision:** DEC-011 — Native mobile via Capacitor (not React Native). Capacitor wraps our existing React SPA in a native shell, reusing 95%+ of the codebase while adding native device API…
71 | Idea: Percy.io GitHub integration for PR status checks | unscheduled | idea | platform |  | idea, platform |  | jisujit | 0 | 2026-02-24 | 2026-04-05 | https://github.com/rent-a-vacation/rav-website/issues/71 | ## Percy Visual Regression as PR Status Check Currently Percy runs in CI but results aren't surfaced as GitHub PR status checks. ### Proposal - [ ] Configure Percy GitHub App integration - [ ] Add Percy status check to PR required checks - [ ] Visual diff approval required before merge - [ ] Document visual review workflow for contributors ### Context Percy snapshots already run on PRs (4 pages: Homepage, Rentals, Login, Signup). This would make visual review a formal gate.

## Summary
Open-issue rollups
By priority
Bucket | Open issues
post-launch | 17
pre-launch | 16
unscheduled | 12
blocked | 2
future | 1
post-beta | 1
By type
Bucket | Open issues
enhancement | 42
(unset) | 2
bug | 2
docs | 2
idea | 1
By area
Bucket | Open issues
platform | 24
experience | 18
(unset) | 2
experience, platform | 2
marketplace | 2
marketplace, vacation-wishes | 1
By milestone
Bucket | Open issues
(no milestone) | 33
Phase 12: Native Mobile (Capacitor) | 9
Growth & Marketing | 2
Launch Readiness | 2
Phase 20: Accounting & Tax | 2
Phase 6: Advanced Features | 1
By label
Bucket | Open issues
enhancement | 42
platform | 26
experience | 20
post-launch | 18
pre-launch | 17
marketplace | 3
blocked | 2
bug | 2
docs | 2
idea | 2
needs-decision | 2
future | 1
post-beta | 1
vacation-wishes | 1

## Legend
Priority chip legend
Chip | Meaning
blocked | Has the `blocked` label — waiting on an external dependency.
pre-launch | Required before public launch.
post-launch | Can wait until after launch.
post-beta | Targeted for after a beta cohort.
future | Long-horizon idea or backlog item.
unscheduled | No tier label set — needs triage.